BBE NEXT FOR GROWTH AIM Incubator Tiger Team Design Hackathon Brief — Week of June 8, Purchase NY

A quick guide to how we’ll spend the 2½ days together. Have a look before June 9 and come ready with the pre-work. We’ll close Define and open Design together in the room.

# 1. Why we’re coming together

PepsiCo’s Better Brand Equity (BBE) quarterly read is foundational, but today it’s slow, disconnected, and underused as a growth lever. Analysts spend 15–20 hours per project stitching data together; reports often read like data dumps; and BBE on its own only tells part of the growth story.

The BBE Next for Growth Tiger Team has a finite charter: reinvent how PepsiCo measures, predicts, and acts on brand equity — and feed that work into a better BGS process and the wider measurement spine. This 2.5-day hackathon is where Define closes and Design begins.

# 2. The problems we’re solving

- The BBE Progress Tracker is misaligned with the broader BBE reporting story. Different views, different numbers, different narratives — analysts spend time reconciling instead of interpreting.

- MDS is read in isolation from Demand and Pricing Power. Equity signals get disconnected from the commercial reality they’re supposed to predict.

- Reports read like a data dump. Insight gets buried; the “so what” doesn’t surface; analysts spend hours building the story manually.

- BBE data on its own only goes so far. Without category context, outcome trajectory, and portfolio role, equity reads can mislead growth decisions.

# 3. The vision for the Quick Report

A reimagined BBE Quick Report that is:

- Interactive — Analysts and brand teams can pressure-test reads, not just consume them.

- Actionable — Equity findings tie directly to growth choices, not just trend lines.

- Insightful — Provocation, not summary. Surfaces the tension worth acting on.

# 4. How we work as a Tiger Team

A tiger team has a finite charter and a clear exit. We’re not a standing committee. We move in stages:

| Define | Design | Develop |
| --- | --- | --- |
| Lock the problem, the user, the success bar. In progress; closes at this hackathon. | Pressure-test the concept, lock the v2 design, decide what’s worth building. This hackathon. | Build, test, hand off to the operating model. Post-hackathon sprints. |

Our working model is

- Agent-assisted intelligence does the heavy lifting on synthesis, pattern detection, and first-draft narrative.

- The data spine — BBE, MDS, Demand, Pricing Power, category context — is what the agent reasons over.

- The human in the loop — Tim, Tracey, Ali, analysts — sets the provocation bar, validates the read, and owns the growth decision.

How we'll spend the time: working-session heavy, light on decks. Decisions happen in the room together.

# 5. What we’re building: agent-assisted intelligence

The BBE Quick Report is the first proof point of a broader system: agent-assisted intelligence that links

- BGS gets sharper inputs from a connected equity-and-outcome read.

- Growth Navigator gets the equity signal woven into the growth process framework, not bolted on.

- The measurement spine gets a connected view of equity, demand, and pricing power — the foundation for predictive, not just diagnostic, measurement.

The bet: If we build BBE Next in isolation, we’ll have a better report. If we build it as the front end of the measurement spine, we’ll have a growth system.

# 6. What success looks like after 2.5 days

By Thursday mid-day, we leave with:

- A locked problem statement — what we’re solving, for whom, why it matters now.

- A prioritized list of use cases — top 3–5, ranked by analyst impact and growth-decision value.

- A draft v2 product concept for the BBE Quick Report — clear evolution from today’s prototype.

- A clear “what we are building vs. not building” — the explicit out-of-scope list matters as much as the in-scope.

- Alignment on how BBE, Growth Navigator, and category context come together as one read.

- MDS, Demand, and Pricing Power framed as one system, not three reports.

- A resolution to the BBE Progress Tracker misalignment — one source of truth, one narrative.

- A 30/60/90 roadmap out of the hackathon — what ships, who owns it, when it lands.

- A first-cut user journey for the analyst using the Quick Report end-to-end.

# 7. Who’s in the room

| Name | Role | Seat |
| --- | --- | --- |
| Kate Schardt | VP, Global Insights | Sponsor |
| Lydia Armstrong | Mktg & Insights Capability Director | Tiger Team Lead |
| Tim McEntaggart | Mktg & Insights Capability Sr Director | Brand / BBE SME |
| Jeremy Wasson | Mktg & Insights Capability Sr Director | MarSci bridge to measurement spine |
| Tracey Neis | Insights CoE | Insight planning / truth serum |
| Ali Levins | Growth Navigator, Marketing Capabilities | BGS + Growth Process Framework |
| Jim Keyt (TBC) | S&T | AIM Enterprise Architecture Lead |
| Brion Goudreau (TBC) | S&T | AIM Incubator S&T Lead |

In addition to the core tiger team, we will bring in 20 to 25 cross-functional and cross-market stakeholders on day 2 of the hackathon to pressure-test the prototype design and sharpen what moves forward.